Project Planning – Sprint / Story Point / Velocity Logic

SB Stocks – Stock Trading Application (MERN)

A Sprint is a fixed period or duration in which a team works to complete a set of tasks.

An Epic is a big task or project that is too large to complete in one sprint. It is broken down into smaller tasks (stories) that can be completed over multiple sprints.

A Story is a small task. It is part of an Epic.

A Story Point is a number that represents how much effort a story takes to complete (usually in the form of a Fibonacci series).

1 – Very Easy task

2 – Normal task

3 – Moderate task

5 – Difficult task

Story Points used: 1, 2, 3, 5 (Fibonacci series)

# Sprint 1 – Project Setup & Database Design

Project & Environment Setup (Epic 1)

Setting up Client and Server project folders (USN1)                    1

Initializing React (Vite) frontend project (USN2)                      2

Initializing Node.js/Express backend project (USN3)                    1

Database Design (Epic 2)

Configuring MongoDB connection (USN4)                                   2

Designing Mongoose Schemas – User, Stock, Transaction, Order (USN5)     3

Total Story Points in Sprint 1 = 1+2+1+2+3 = 9

# Sprint 2 – User Authentication

Registration & Login (Epic 3)

Building user registration API (USN6)                                  3

Building user login API (USN7)                                         2

Building authentication middleware for protected routes (USN8)         3

Authentication UI (Epic 4)

Building Register component (USN9)                                     2

Building Login component (USN10)                                       2

Total Story Points in Sprint 2 = 3+2+3+2+2 = 12

# Sprint 3 – Stock Listings & Market Data

Stock Data Backend (Epic 5)

Building Stock model/schema (USN11)                                    2

Integrating real-time & historical market data source (USN12)          5

Building stock controller and routes (USN13)                           3

Stock UI (Epic 6)

Building stock listing/search page (USN14)                             3

Building StockChart component (USN15)                                  5

Total Story Points in Sprint 3 = 2+5+3+3+5 = 18

# Sprint 4 – Paper Trading & Portfolio

Order & Transaction Backend (Epic 7)

Building Order model and controller (USN16)                            3

Building Transaction model and controller (USN17)                      3

Implementing Buy/Sell logic and virtual balance updates (USN18)         5

Portfolio & History UI (Epic 8)

Building Portfolio page (USN19)                                        3

Building Transaction History page (USN20)                              2

Total Story Points in Sprint 4 = 3+3+5+3+2 = 16

# Sprint 5 – Admin Module & Testing

Admin Module (Epic 9)

Building admin authentication (USN21)                                  2

Building Admin dashboard and Users page (USN22)                        3

Building All Orders / All Transactions pages (USN23)                   3

Testing & Deployment (Epic 10)

Functional testing across all modules (USN24)                          2

Performance testing and bug fixes (USN25)                              3

Total Story Points in Sprint 5 = 2+3+3+2+3 = 13

# Total Story Points

Sprint 1 = 9

Sprint 2 = 12

Sprint 3 = 18

Sprint 4 = 16

Sprint 5 = 13

## Velocity

Velocity = Total Story Points Completed / Number of Sprints

Total Story Points = 9 + 12 + 18 + 16 + 13 = 68

Number of Sprints = 5

Velocity = 68 / 5 = 13.6 (Story Points per Sprint)

Your team's velocity is 13.6 Story Points per Sprint.